## Sheet1
Task |  | Already complete? | Spring '24 |  |  |  |  | Summer '24 |  |  | Fall '24
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Code Transformations | Introduce concepts
Create proof-of-concept framework
Benchmark against SOTA on standard optimization test problems
Document end-to-end aircraft design case | bar: Spring '24 Jan to Spring '24 Apr
Explore additional framework features to support interpretability | bar: Spring '24 Jan to Summer '24 Jun
Provide a review of practical feasibility of code transformation paradigm | bar: Spring '24 May to Fall '24 Sep
Traceable Physics Models | Build the models specified in Table 3.2
Document models thoroughly | bar: Spring '24 Mar to Spring '24 May
Document challenges encountered during model implementation and any workarounds required | bar: Spring '24 Apr to Summer '24 Jun
Sparsity Tracing via NaN-Propagation | Introduce concepts | bar: Spring '24 Jan to Spring '24 Feb
Build a minimum-working code example to demonstrate feasibility | bar: Spring '24 Mar to Spring '24 Apr
Demonstrate this code example on a simple black-box aerospace-related analysis | bar: Spring '24 May to Summer '24 Jun
Physics-Informed ML Surrogates for Black-Box Models | Create ML surrogates for XFoil
Demonstrate optimization through these surrogates in a code transformations framework
Aircraft System Identification | Demonstrate application of code transformations framework to system identification
Thesis Writing